## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
| Create Account | As a user I want to create an account in so that I can order food and interact with the application | High | Must | 1 | Done
| View Restaurants | As a user I want to view restaurants so that I can see which restaurant is available to get food from | High | Must | 1 | Done
| Search Restaurants | As a user I want to search for restaurants so that I can easily find the restaurant I want | Medium | Should | 1 | Done
| View Menu | As a user I want to view the menu so that I can see the available meals and interact with them | High | Must | 2 | Work In Progress
| Add to Cart | As a user I want to be able to add to cart so that I can purchase food and collect them in one place | High | Should | 2 | Work In Progress
| Purchase | As a user I want to be able to purchase items so that I can pay for the food that is delivered | High | Should | 2 | Work In Progress
| Restaurant views order | As a restaurant worker I want to be able to view orders so that I can prepare them to be delivered | Medium | Must | 3 | To Be Started
| Restaurant marks order as delivered | As a restaurant worker I want to be able to mark orders as delivered so that I don’t have to prepare it and send it again for the same user | Medium | Could | 3 | To Be Started