## Task Board
To Do | In Progress | Testing | Done
Restaurant view Order | Add to Cart | View Menu | Create Account
Restaurant marks order as delivered | Purchase |  | View Restaurants
Search Restaurants

## Burndown Chart
Tasks | Iterations | Ideal tasks remaining | Actual tasks remaining
Create Account | Week 1 | 7 | 7
View Restaurants | Week 2 | 6 | 6
Search Restaurants | Week 3 | 5 | 6
View Menu | Week 4 | 4 | 5
Add to Cart | Week 5 | 3 | 5
Purchase | Week 6 | 2 | 2
Restaurant views order | Week 7 | 1 | 1
Restaurant marks order as delivered | Week 8 | 0 | 0